## Sheet1
TASK NAME | DURATION (DAYS) | Expected Duration (DAYS)
Software Development | 190 | 165
Scope | 4 | 4
User Analysis | 30 | 30
Design Analysis | 44 | 44
Sprint 1
Backlog | 1 | 1
Coding and Development | 27 | 21
Release phase, Evaluation and Debugging | 7 | 7
Sprint 2
Backlog | 1 | 1
Coding and Development | 24 | 21
Release phase, Evaluation and Debugging | 7 | 7
Sprint 3
Backlog | 1 | 1
Coding and Development | 37 | 21
Release phase, Evaluation and Debugging | 7 | 7